## Sheet1
Activity | Description | Activity Predecessor | Optimistic Time Estimate | Most likely Time Estimate | Pessimistic Time Estimate | Expected Time | Normal Cost | Crash Time | Crash Cost
1 | General design | - | 6 | 10 | 24 | 11.6667 | 65700 | 10 | 72500
2 | Engine design | - | 20 | 35 | 60 | 36.6667 | 285000 | 30 | 322500
3 | Airframe design | 1 | 5 | 17 | 33 | 17.6667 | 93400 | 15 | 103600
4 | Avionics design | 1 | 2 | 8 | 21 | 9.1667 | 74200 | 8 | 92000
5 | Develop test engine | 2 | 6 | 9 | 15 | 9.5 | 87200 | 9.5 | 87200
6 | Develop test airframe | 3 | 7 | 12 | 17 | 12 | 85000 | 10 | 97000
7 | Develop interim avionics | 4 | 6 | 16 | 27 | 16.1667 | 88300 | 14 | 124000
8 | Engine Development | 2 | 18 | 25 | 42 | 26.6667 | 236400 | 25 | 297400
9 | Assemble test aircraft | 5, 6, 7 | 5 | 8 | 11 | 8 | 62900 | 8 | 62900
10 | Test avionics | 4 | 4 | 11 | 16 | 10.6667 | 63900 | 10 | 79900
11 | Engine/airframe flight trials | 9 | 5 | 10 | 13 | 9.6667 | 77600 | 9.6667 | 77600
12 | Avionics flight trails | 10 | 5 | 9 | 26 | 11.1667 | 69100 | 10 | 85100
13 | Engine production | 8 | 10 | 15 | 18 | 14.6667 | 109800 | 14.6667 | 109800
14 | Airframe production | 11 | 11 | 14 | 21 | 14.6667 | 112500 | 14.6667 | 112500
15 | Avionics production | 11, 12 | 12 | 16 | 26 | 17 | 97200 | 15 | 105000
16 | Final assembly/finish | 13, 14, 15 | 3 | 5 | 6 | 4.8333 | 25000 | 4.8333 | 25000

## Sheet1 (2)
Activity | Description | Expected Time | Normal Cost | Crash Time | Crash Cost
1 | General design | 11.6667 | 65700 | 10 | 72500
2 | Engine design | 36.6667 | 285000 | 30 | 322500
3 | Airframe design | 17.6667 | 93400 | 15 | 103600
4 | Avionics design | 9.1667 | 74200 | 8 | 92000
5 | Develop test engine | 9.5 | 87200 | 9.5 | 87200
6 | Develop test airframe | 12 | 85000 | 10 | 97000
7 | Develop interim avionics | 16.1667 | 88300 | 14 | 124000
8 | Engine Development | 26.6667 | 236400 | 25 | 297400
9 | Assemble test aircraft | 8 | 62900 | 8 | 62900
10 | Test avionics | 10.6667 | 63900 | 10 | 79900
11 | Engine/airframe flight trials | 9.6667 | 77600 | 9.6667 | 77600
12 | Avionics flight trails | 11.1667 | 69100 | 10 | 85100
13 | Engine production | 14.6667 | 109800 | 14.6667 | 109800
14 | Airframe production | 14.6667 | 112500 | 14.6667 | 112500
15 | Avionics production | 17 | 97200 | 15 | 105000
16 | Final assembly/finish | 4.8333 | 25000 | 4.8333 | 25000