## Q1
Q 1: Construct the project network (activity-on-node diagram). List all the paths of the project network.
Paths :
1) | A-B-I-J-K
2) | A-B-F-J-K
3) | A-C-H-J-K
4) | A-C-D-E-H-J-K
5) | A-C-D-E-F-J-K
6) | A-C-D-G-J-K

## Q2
Q 2: Using the “most likely” time estimates, what is the completion time for this project? Identify the critical path(s) of the project. Identify the critical and non-critical tasks. What is the cost of the project?
Task | Most Likely Time | Early Start | Early Finish | Late Start | Late Finish | LS-ES | LF-EF | Critical tasks | Normal Costs
A | 3 | 0 | 3 | 0 | 3 | 0 | 0 | Critical | 10000
B | 7 | 3 | 10 | 18 | 25 | 15 | 15 |  | 20000
C | 6 | 3 | 9 | 3 | 9 | 0 | 0 | Critical | 15000
D | 7 | 9 | 16 | 9 | 16 | 0 | 0 | Critical | 45000
E | 9 | 16 | 25 | 16 | 25 | 0 | 0 | Critical | 10000
F | 5 | 25 | 30 | 25 | 30 | 0 | 0 | Critical | 15000
G | 6 | 16 | 22 | 24 | 30 | 8 | 8 |  | 20000
H | 4 | 25 | 29 | 26 | 30 | 1 | 1 |  | 10000
I | 2 | 10 | 12 | 28 | 30 | 18 | 18 |  | 5000
J | 4 | 30 | 34 | 30 | 34 | 0 | 0 | Critical | 40000
K | 3 | 34 | 37 | 34 | 37 | 0 | 0 | Critical | 15000
205000
Completion Time |  | 37
Cost of the project |  | 205000
| Paths | Duration
1) | A-B-I-J-K | 19
2) | A-B-F-J-K | 22
3) | A-C-H-J-K | 20
4) | A-C-D-E-H-J-K | 36
5) | A-C-D-E-F-J-K | 37 | CRITICAL PATH
6) | A-C-D-G-J-K | 29

## Q3
Q 3: Using the “most optimistic” time estimates, what is the completion time for this project? Identify the critical path(s) of the project. Identify the critical and non-critical tasks. What is the cost of the project?
Task | Most Optimistic Time | Early Start | Early Finish | Late Start | Late Finish | LS-ES | LF-EF | Critical tasks | Normal Costs
A | 2 | 0 | 2 | 0 | 2 | 0 | 0 | Critical | 10000
B | 4 | 2 | 6 | 16 | 20 | 14 | 14 |  | 20000
C | 5 | 2 | 7 | 2 | 7 | 0 | 0 | Critical | 15000
D | 6 | 7 | 13 | 7 | 13 | 0 | 0 | Critical | 45000
E | 7 | 13 | 20 | 13 | 20 | 0 | 0 | Critical | 10000
F | 4 | 20 | 24 | 20 | 24 | 0 | 0 | Critical | 15000
G | 3 | 13 | 16 | 21 | 24 | 8 | 8 |  | 20000
H | 2 | 20 | 22 | 22 | 24 | 2 | 2 |  | 10000
I | 2 | 6 | 8 | 22 | 24 | 16 | 16 |  | 5000
J | 3 | 24 | 27 | 24 | 27 | 0 | 0 | Critical | 40000
K | 2 | 27 | 29 | 27 | 29 | 0 | 0 | Critical | 15000
205000
Completion Time |  | 29
Cost of the project |  | 205000
| Paths | Duration
1) | A-B-I-J-K | 13
2) | A-B-F-J-K | 15
3) | A-C-H-J-K | 14
4) | A-C-D-E-H-J-K | 27
5) | A-C-D-E-F-J-K | 29 | CRITICAL PATH
6) | A-C-D-G-J-K | 21

## Q-4
Q 4: Using the “most pessimistic” time estimates, what is the completion time for this project? Identify the critical path(s) of the project. Identify the critical and non-critical tasks. What is the cost of the project?
Task | Most Pessimistic Time | Early Start | Early Finish | Late Start | Late Finish | LS-ES | LF-EF | Critical tasks | Normal Costs
A | 4 | 0 | 4 | 0 | 4 | 0 | 0 | Critical | 10000
B | 10 | 4 | 14 | 30 | 40 | 26 | 26 |  | 20000
C | 9 | 4 | 13 | 4 | 13 | 0 | 0 | Critical | 15000
D | 16 | 13 | 29 | 13 | 29 | 0 | 0 | Critical | 45000
E | 10 | 29 | 39 | 29 | 39 | 0 | 0 | Critical | 10000
F | 6 | 39 | 45 | 40 | 46 | 1 | 1 |  | 15000
G | 10 | 29 | 39 | 36 | 46 | 7 | 7 |  | 20000
H | 7 | 39 | 46 | 39 | 46 | 0 | 0 | Critical | 10000
I | 2 | 14 | 16 | 44 | 46 | 30 | 30 |  | 5000
J | 14 | 46 | 60 | 46 | 60 | 0 | 0 | Critical | 40000
K | 4 | 60 | 64 | 60 | 64 | 0 | 0 | Critical | 15000
205000
Completion Time |  | 64
Cost of the project |  | 205000
| Paths | Duration
1) | A-B-I-J-K | 34
2) | A-B-F-J-K | 38
3) | A-C-H-J-K | 38
4) | A-C-D-E-H-J-K | 64 | CRITICAL PATH (NOTE THE CHANGE)
5) | A-C-D-E-F-J-K | 63
6) | A-C-D-G-J-K | 57

## Q-5
Q 5: If we account for the uncertainty in the duration of the tasks, what is the estimated completion time for this project? (Use the “expected time” estimates for your calculations). Identify the critical path(s) of the project. Identify the critical and non-critical tasks. What is the cost of the project? Compute the range of the project durations by accounting for the uncertainty in the duration of the tasks.
EQUAL WEIGHTS ((a) Use Triangular distribution to find the expected values of activity time.)
Task | Most Optimistic Time | Most Likely Time | Most Pessimistic Time | Expected Time | Early Start | Early Finish | Late Start | Late Finish | LS-ES | LF-EF | Critical Tasks | Normal Costs
A | 2 | 3 | 4 | 3 | 0 | 3 | 0 | 3 | 0 | 0 | Critical | 10000
B | 4 | 7 | 10 | 7 | 3 | 10 | 21 | 28 | 18 | 18 |  | 20000
C | 5 | 6 | 9 | 6.6667 | 3 | 9.6667 | 3 | 9.6667 | 0 | 0 | Critical | 15000
D | 6 | 7 | 16 | 9.6667 | 9.6667 | 19.3333 | 9.6667 | 19.3333 | 0 | 0 | Critical | 45000
E | 7 | 9 | 10 | 8.6667 | 19.3333 | 28 | 19.3333 | 28 | 0 | 0 | Critical | 10000
F | 4 | 5 | 6 | 5 | 28 | 33 | 28 | 33 | 0 | 0 | Critical | 15000
G | 3 | 6 | 10 | 6.3333 | 19.3333 | 25.6667 | 26.6667 | 33 | 7.3333 | 7.3333 |  | 20000
H | 2 | 4 | 7 | 4.3333 | 28 | 32.3333 | 28.6667 | 33 | 0.66667 | 0.66667 |  | 10000
I | 2 | 2 | 2 | 2 | 10 | 12 | 31 | 33 | 21 | 21 |  | 5000
J | 3 | 4 | 14 | 7 | 33 | 40 | 33 | 40 | 0 | 0 | Critical | 40000
K | 2 | 3 | 4 | 3 | 40 | 43 | 40 | 43 | 0 | 0 | Critical | 15000
205000
Completion time |  | 43
Cost of the project |  | 205000
Paths :
1) | A-B-I-J-K
2) | A-B-F-J-K
3) | A-C-H-J-K
4) | A-C-D-E-H-J-K
5) | A-C-D-E-F-J-K | 43 | CRITICAL PATH
6) | A-C-D-G-J-K
(b) Use Beta distribution to find the expected values of activity time.
Task | Most Optimistic Time | Most Likely Time | Most Pessimistic Time | Expected Time | Early Start | Early Finish | Late Start | Late Finish | LS-ES | LF-EF | Critical Tasks | Normal Costs
A | 2 | 3 | 4 | 3 | 0 | 3 | 0 | 3 | 0 | 0 | Critical | 10000
B | 4 | 7 | 10 | 7 | 3 | 10 | 19.5 | 26.5 | 16.5 | 16.5 |  | 20000
C | 5 | 6 | 9 | 6.3333 | 3 | 9.3333 | 3 | 9.3333 | 0 | 0 | Critical | 15000
D | 6 | 7 | 16 | 8.3333 | 9.3333 | 17.6667 | 9.3333 | 17.6667 | 0 | 0 | Critical | 45000
E | 7 | 9 | 10 | 8.8333 | 17.6667 | 26.5 | 17.6667 | 26.5 | 0 | 0 | Critical | 10000
F | 4 | 5 | 6 | 5 | 26.5 | 31.5 | 26.5 | 31.5 | 0 | 0 | Critical | 15000
G | 3 | 6 | 10 | 6.1667 | 17.6667 | 23.8333 | 25.3333 | 31.5 | 7.6667 | 7.6667 |  | 20000
H | 2 | 4 | 7 | 4.1667 | 26.5 | 30.6667 | 27.3333 | 31.5 | 0.83333 | 0.83333 |  | 10000
I | 2 | 2 | 2 | 2 | 10 | 12 | 29.5 | 31.5 | 19.5 | 19.5 |  | 5000
J | 3 | 4 | 14 | 5.5 | 31.5 | 37 | 31.5 | 37 | 0 | 0 | Critical | 40000
K | 2 | 3 | 4 | 3 | 37 | 40 | 37 | 40 | 0 | 0 | Critical | 15000
205000
Completion time |  | 40
Cost of the project |  | 205000
Paths :
1) | A-B-I-J-K | 20.5
2) | A-B-F-J-K | 23.5
3) | A-C-H-J-K | 22
4) | A-C-D-E-H-J-K | 39.1667
5) | A-C-D-E-F-J-K | 40 | CRITICAL PATH
6) | A-C-D-G-J-K | 32.3333

## Q#6-7-8
Q 6: Compute the variance of the activities as well as the critical path and comment of the risks involved.
Task | Estimated Duration | Early Start | Early Finish | Late Start | Late Finish | LS-ES | LF-EF
A | 3 | 0 | 3 | 0 | 3 | 0 | 0 | Critical task
B | 7 | 3 | 10 | 20 | 27 | 17 | 17
C | 6 | 3 | 9 | 3 | 9 | 0 | 0 | Critical task
D | 8 | 9 | 18 | 9 | 18 | 0 | 0 | Critical task
E | 9 | 18 | 27 | 18 | 27 | 0 | 0 | Critical task
F | 5 | 27 | 32 | 27 | 32 | 0 | 0 | Critical task
G | 6 | 18 | 24 | 25 | 32 | 8 | 8
H | 4 | 27 | 31 | 27 | 32 | 1 | 1
I | 2 | 10 | 12 | 30 | 32 | 20 | 20
J | 6 | 32 | 37 | 32 | 37 | 0 | 0 | Critical task
K | 3 | 37 | 40 | 37 | 40 | 0 | 0 | Critical task
Task | Most Optimistic | Most Likely | Most Pessimistic | Expected Duration | Variance in the Duration
A | 2 | 3 | 4 | 3 | 0.11111
B | 4 | 7 | 10 | 7 | 1
C | 5 | 6 | 9 | 6.3333 | 0.44444
D | 6 | 7 | 16 | 8.3333 | 2.7778
E | 7 | 9 | 10 | 8.8333 | 0.25
F | 4 | 5 | 6 | 5 | 0.11111
G | 3 | 6 | 10 | 6.1667 | 1.3611
H | 2 | 4 | 7 | 4.1667 | 0.69444
I | 2 | 2 | 2 | 2 | 0
J | 3 | 4 | 14 | 5.5 | 3.3611
K | 2 | 3 | 4 | 3 | 0.11111
[5 empty] | 7.1667 | = this is the variance of the critical path
[5 empty] | 2.6771 | = this is the standard dev. of the critical path
Desired due date | Prob. of Completion
30 | 0.009369%
31 | 0.03871%
32 | 0.1402%
33 | 0.4464%
34 | 1.25%
35 | 3.09%
36 | 6.756%
37 | 13.12%
38 | 22.75%
39 | 35.44%
40 | 50%
41 | 64.56%
42 | 77.25%
43 | 86.88%
44 | 93.24%
45 | 96.91%
46 | 98.75%
47 | 99.55%
48 | 99.86%
Q 7: What is the probability that the project can be completed in 40 weeks? OR What is the level of confidence that the project can be completed by the mean duration of the 40 weeks?
Use the excel function NORMDIST (X, mean, standard deviation, cumulative frequency) to compute the probability.
Q 8: What is the probability that the project can be completed in 35 weeks? OR What is the level of confidence that the project can be completed by the mean duration of the 35 weeks?
Use the excel function NORMDIST (X, mean, standard deviation, cumulative frequency) to compute the probability.

## Q#9
Q 9: What is the impact of the project completion time on the probability of the completion of the project? Illustrate through a plot.
Target Date | Level of Confidence
30 | 0.009369%
31 | 0.03871%
32 | 0.1402%
33 | 0.4464%
34 | 1.25%
35 | 3.09%
36 | 6.756%
37 | 13.12%
38 | 22.75%
39 | 35.44%
40 | 50%
41 | 64.56%
42 | 77.25%
43 | 86.88%
44 | 93.24%
45 | 96.91%
46 | 98.75%
47 | 99.55%
48 | 99.86%
49 | 99.96%
Task | Estimated Duration | Early Start | Early Finish | Late Start | Late Finish | LS-ES | LF-EF
A | 3 | 0 | 3 | 0 | 3 | 0 | 0 | Critical task |  | Paths
B | 7 | 3 | 10 | 20 | 27 | 17 | 17 |  |  | A-B-I-J-K
C | 6 | 3 | 9 | 3 | 9 | 0 | 0 | Critical task |  | A-B-F-J-K
D | 8 | 9 | 18 | 9 | 18 | 0 | 0 | Critical task |  | A-C-H-J-K
E | 9 | 18 | 27 | 18 | 27 | 0 | 0 | Critical task |  | A-C-D-E-H-J-K
F | 5 | 27 | 32 | 27 | 32 | 0 | 0 | Critical task | Results that thee critical path is = | A-C-D-E-F-J-K
G | 6 | 18 | 24 | 25 | 32 | 8 | 8 |  |  | A-C-D-G-J-K
H | 4 | 27 | 31 | 27 | 32 | 1 | 1
I | 2 | 10 | 12 | 30 | 32 | 20 | 20
J | 6 | 32 | 37 | 32 | 37 | 0 | 0 | Critical task
K | 3 | 37 | 40 | 37 | 40 | 0 | 0 | Critical task
Task | Most Optimistic | Most Likely | Most Pessimistic | Expected Duration | Variance in the Duration
A | 2 | 3 | 4 | 3 | 0.11111
B | 4 | 7 | 10 | 7 | 1
C | 5 | 6 | 9 | 6.3333 | 0.44444
D | 6 | 7 | 16 | 8.3333 | 2.7778
E | 7 | 9 | 10 | 8.8333 | 0.25
F | 4 | 5 | 6 | 5 | 0.11111
G | 3 | 6 | 10 | 6.1667 | 1.3611
H | 2 | 4 | 7 | 4.1667 | 0.69444
I | 2 | 2 | 2 | 2 | 0
J | 3 | 4 | 14 | 5.5 | 3.3611
K | 2 | 3 | 4 | 3 | 0.11111
[5 empty] | 7.1667 | = this is the variance of the critical path
[5 empty] | 2.6771 | = this is the standard deviation of the variance of the critical path

## Q#10
10: The project manager would like to reduce the duration of the project to 35 weeks. Clearly indicate the activities to crash, the resulting expected project time and associated costs at each step.
Task | Normal Costs | Expected | Crash Costs | Crash Time | Marginal Cost/week | No. of week that can be expedited
A | 10000 | 3 | 10000 | 3
B | 20000 | 7 | 25000 | 6 | 5000 | 1
C | 15000 | 6.3333 | 30000 | 5 | 11250 | 1.3333
D | 45000 | 8.3333 | 65000 | 6 | 8571.4286 | 2.3333
E | 10000 | 8.8333 | 20000 | 8 | 12000 | 0.83333
F | 15000 | 5 | 18000 | 4 | 3000 | 1
G | 20000 | 6.1667 | 30000 | 4 | 4615.3846 | 2.1667
H | 10000 | 4.1667 | 15000 | 3 | 4285.7143 | 1.1667
I | 5000 | 2 | 5000 | 2
J | 40000 | 5.5 | 50000 | 5 | 20000 | 0.5
K | 15000 | 3 | 25000 | 2 | 10000 | 1
Paths | Duration | F | F & H | D | D | D | K | C
|  | 0.83 | 0.17 | 1 | 1 | 0.33 | 1 | 0.67
A-B-I-J-K | 20.5 | 20.5 | 20.5 | 20.5 | 20.5 | 20.5 | 19.5 | 19.5
A-B-F-J-K | 23.5 | 22.67 | 22.5 | 22.5 | 22.5 | 22.5 | 21.5 | 21.5
A-C-H-J-K | 22 | 22 | 21.83 | 21.83 | 21.83 | 21.5 | 20.5 | 19.83
A-C-D-E-H-J-K | 39.1667 | 39.1667 | 38.9967 | 37.9967 | 36.9967 | 36.6667 | 35.6667 | 34.9967
A-C-D-E-F-J-K | 40 | 39.17 | 39 | 38 | 37 | 36.67 | 35.67 | 35
A-C-D-G-J-K | 32.3333 | 32.3333 | 32.3333 | 31.3333 | 30.3333 | 30.0033 | 29.0033 | 28.3333
Project Duration | 40 | 39.17 | 39 | 38 | 37 | 36.67 | 35.67 | 35
Crash Cost |  | 2490 | 1238.5714 | 8571.4286 | 8571.4286 | 2828.5714 | 10000 | 7537.5
Cumul. Crash Cost |  | 2490 | 3728.5714 | 12300 | 20871.4286 | 23700 | 33700 | 41237.5
Total Proj. Cost | 205000 | 207490 | 208728.5714 | 217300 | 225871.4286 | 228700 | 238700 | 246237.5
Answer: The cost of project with a 35 week duration, using the expected time estimate, is $247,238

## Q#11
Q 11: Based on the information provided, what is the maximum crashing that can be achieved. Clearly indicate the activities to crash, the resulting expected project time and associated costs at each step.
Task | Normal Costs | Expected | Crash Costs | Crash Time | Marginal Cost/week | No. of week that can be expedited
A | 10000 | 3 | 10000 | 3
B | 20000 | 7 | 25000 | 6 | 5000 | 1
C | 15000 | 6.3333 | 30000 | 5 | 11250 | 1.3333
D | 45000 | 8.3333 | 65000 | 6 | 8571.4286 | 2.3333
E | 10000 | 8.8333 | 20000 | 8 | 12000 | 0.83333
F | 15000 | 5 | 18000 | 4 | 3000 | 1
G | 20000 | 6.1667 | 30000 | 4 | 4615.3846 | 2.1667
H | 10000 | 4.1667 | 15000 | 3 | 4285.7143 | 1.1667
I | 5000 | 2 | 5000 | 2
J | 40000 | 5.5 | 50000 | 5 | 20000 | 0.5
K | 15000 | 3 | 25000 | 2 | 10000 | 1
Paths | Duration | F | F & H | D | D | D | K | C | E | J
|  | 0.83 | 0.17 | 1 | 1 | 0.33 | 1 | 1.33 | 0.83 | 0.5
A-B-I-J-K | 20.5 | 20.5 | 20.5 | 20.5 | 20.5 | 20.5 | 19.5 | 19.5 | 19.5 | 19
A-B-F-J-K | 23.5 | 22.67 | 22.5 | 22.5 | 22.5 | 22.5 | 21.5 | 21.5 | 21.5 | 21
A-C-H-J-K | 22 | 22 | 21.83 | 21.83 | 21.83 | 21.5 | 20.5 | 19.17 | 19.17 | 18.67
A-C-D-E-H-J-K | 39.1667 | 39.1667 | 38.9967 | 37.9967 | 36.9967 | 36.6667 | 35.6667 | 34.3367 | 33.5067 | 33.0067
A-C-D-E-F-J-K | 40 | 39.17 | 39 | 38 | 37 | 36.67 | 35.67 | 34.34 | 33.51 | 33.01
A-C-D-G-J-K | 32.3333 | 32.3333 | 32.3333 | 31.3333 | 30.3333 | 30.0033 | 29.0033 | 28.3333 | 28.3333 | 27.8333
Project Duration | 40 | 39.17 | 39 | 38 | 37 | 36.67 | 35.67 | 34.34 | 33.51 | 33.01
Crash Cost |  | 2490 | 1238.5714 | 8571.4286 | 8571.4286 | 2828.5714 | 10000 | 14962.5 | 9960 | 10000
Cumul. Crash Cost |  | 2490 | 3728.5714 | 12300 | 20871.4286 | 23700 | 33700 | 48662.5 | 58622.5 | 68622.5
Total Proj. Cost | 205000 | 207490 | 208728.5714 | 217300 | 225871.4286 | 228700 | 238700 | 253662.5 | 263622.5 | 273622.5
Answer: The cost of project with a 33 week duration, using the expected time estimate, is $273,623

## Q#12
9) Plot the crashing cost curve (project duration vs. total project cost). What insights do this curve provide?
Project Duration | 37 | 36 | 35 | 34 | 33 | 32
Total Proj. Cost | 205000 | 208000 | 218000 | 228000 | 243000 | 263000
Project Duration | 40 | 39.17 | 39 | 38 | 37 | 36.67 | 35.67 | 34.34 | 33.51 | 33.01
Total Proj. Cost | 205000 | 207490 | 208728.5714 | 217300 | 225871.4286 | 228700 | 238700 | 253662.5 | 263622.5 | 273622.5
Insight: Planning under uncertainity adds to the project cost.

## Q14
Q 11: The project manager wanted to see the impact on the crashing solution if the expected time for task D (development) was decreased to seven weeks. Clearly indicate the activities to crash, the resulting expected project time and associated costs at each step.
Task | Normal Costs | Expected Time | Crash Costs | Crash Time | Marginal Cost/week | No. of week that can be expedited
A | 10000 | 3 | 10000 | 3
B | 20000 | 7 | 25000 | 6 | 5000 | 1
C | 15000 | 6.3333 | 30000 | 5 | 11250 | 1.3333
D | 45000 | 7 | 65000 | 6 | 20000 | 1
E | 10000 | 8.8333 | 20000 | 8 | 12000 | 0.83333
F | 15000 | 5 | 18000 | 4 | 3000 | 1
G | 20000 | 6.1667 | 30000 | 4 | 4615.3846 | 2.1667
H | 10000 | 4.1667 | 15000 | 3 | 4285.7143 | 1.1667
I | 5000 | 2 | 5000 | 2
J | 40000 | 5.5 | 50000 | 5 | 20000 | 0.5
K | 15000 | 3 | 25000 | 2 | 10000 | 1
Paths | Duration | F | F & H | K | C | E | D | J
|  | 0.84 | 0.16 | 1 | 1.33 | 0.83 | 1 | 0.5
A-B-I-J-K | 20.5 | 20.5 | 20.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19
A-B-F-J-K | 23.5 | 22.67 | 22.5 | 21.5 | 21.5 | 21.5 | 21.5 | 21
A-C-H-J-K | 22 | 22 | 21.83 | 20.83 | 19.5 | 19.5 | 19.5 | 19
A-C-D-E-H-J-K | 37.8333 | 37.8333 | 37.6733 | 36.6733 | 35.3433 | 34.5133 | 33.5133 | 33.0133
A-C-D-E-F-J-K | 38.6667 | 37.8267 | 37.6667 | 36.6667 | 35.3367 | 34.5067 | 33.5067 | 33.0067
A-C-D-G-J-K | 31 | 31 | 31 | 30 | 28.67 | 28.67 | 27.67 | 27.17
Project Duration | 40 | 39.17 | 39 | 38 | 35.67 | 34.34 | 33.51 | 33.01
Crash Cost |  | 2520 | 1165.7143 | 10000 | 14962.5 | 9960 | 20000 | 10000
Cumul. Crash Cost |  | 2520 | 3685.7143 | 13685.7143 | 28648.2143 | 38608.2143 | 58608.2143 | 68608.2143
Total Proj. Cost | 205000 | 207520 | 208685.7143 | 218685.7143 | 233648.2143 | 243608.2143 | 263608.2143 | 273608.2143

## Q15
Q 15: Analyze the impact on the crashing solution if the expected time for task B (market assessment) was increased from seven to nine weeks whereas the expected time for task D (development) was decreased to seven weeks simultaneously. Clearly indicate the activities to crash, the resulting expected project time and associated costs at each step.
Note that activity B has a slack of 15 weeks. The change in duration in activity B by 2 weeks will not affect in any way the crash costs because activity B is not on the critical path. The previous Question (Q11) has illustrated the effect of decreasing the expected time from 8.33 to 7 weeks. Hence the previous crashing plan is still applicable in this situation.

## Q#16
Q16: If we ignore the uncertainty in the duration of the tasks, (i.e. use the “most likely time” estimates for your calculations), clearly indicate the activities to crash, the resulting expected project time and associated costs at each step.
Task | Normal Costs | Most Likely Time | Crash Costs | Crash Time | Marginal Cost/week | No. of week that can be expedited
A | 10000 | 3 | 10000 | 3
B | 20000 | 7 | 25000 | 6 | 5000 | 1
C | 15000 | 6 | 30000 | 5 | 15000 | 1
D | 45000 | 7 | 65000 | 6 | 20000 | 1
E | 10000 | 9 | 20000 | 8 | 10000 | 1
F | 15000 | 5 | 18000 | 4 | 3000 | 1
G | 20000 | 6 | 30000 | 4 | 5000 | 2
H | 10000 | 4 | 15000 | 3 | 5000 | 1
I | 5000 | 2 | 5000 | 2
J | 40000 | 4 | 50000 | 5
K | 15000 | 3 | 25000 | 2 | 10000 | 1
Paths | Duration | F (1W) | E (1W)
|  | 1 | 1
A-B-I-J-K | 19 | 19 | 19
A-B-F-J-K | 22 | 21 | 20
A-C-H-J-K | 20 | 20 | 20
A-C-D-E-H-J-K | 36 | 36 | 35
A-C-D-E-F-J-K | 37 | 36 | 35
A-C-D-G-J-K | 29 | 29 | 29
Project Duration | 37 | 36 | 35
Crash Cost |  | 3000 | 10000
Cumul. Crash Cost |  | 3000 | 13000
Total Proj. Cost | 205000 | 208000 | 218000
Answer: The cost of project with a 35 week duration, using the most likely time estimate, is $218,000.