## Project Description
Weights | 16.67% | 66.67% | 16.67%
Task | Most Optimistic | Most Likely | Most Pessimistic | Wt. Avg. TIME ESTIMATE
A | 2 | 3 | 4 | 3
B | 4 | 7 | 10 | 7
C | 5 | 6 | 9 | 6.3333
D | 6 | 7 | 16 | 8.3333
E | 7 | 9 | 10 | 8.8333
F | 4 | 5 | 6 | 5
G | 3 | 6 | 10 | 6.1667
H | 2 | 4 | 7 | 4.1667
I | 2 | 2 | 2 | 2
J | 3 | 4 | 14 | 5.5
K | 2 | 3 | 4 | 3

## Project Crash Data
Task | Normal Costs | Expected Time | Crash Costs | Crash Time
A | 10000 |  | 10000 | 3
B | 20000 |  | 25000 | 6
C | 15000 |  | 30000 | 5
D | 45000 |  | 65000 | 6
E | 10000 |  | 20000 | 8
F | 15000 |  | 18000 | 4
G | 20000 |  | 30000 | 4
H | 10000 |  | 15000 | 3
I | 5000 |  | 5000 | 2
J | 40000 |  | 50000 | 5
K | 15000 |  | 25000 | 2
| 205000 |  | 293000

## Q2Q3Q4Q5
MOST LIKELY TIME ESTIMATE | [8 empty] | Normal Costs
Task | Most Likely | Early Start | Early Finish | Late Start | Late Finish | Slack=LS-ES | Slack= LF-EF |  | 10000
A | 3 | 0 | 3 | 0 | 3 | 0 | 0 | critical | 20000 | 37
B | 7 | 3 | 10 | 18 | 25 | 15 | 15 | non-critical | 15000
C | 6 | 3 | 9 | 3 | 9 | 0 | 0 | critical | 45000
D | 7 | 9 | 16 | 9 | 16 | 0 | 0 | critical | 10000
E | 9 | 16 | 25 | 16 | 25 | 0 | 0 | critical | 15000
F | 5 | 25 | 30 | 25 | 30 | 0 | 0 | critical | 20000
G | 6 | 16 | 22 | 24 | 30 | 8 | 8 | non-critical | 10000
H | 4 | 25 | 29 | 26 | 30 | 1 | 1 | non-critical | 5000
I | 2 | 10 | 12 | 28 | 30 | 18 | 18 | non-critical | 40000
J | 4 | 30 | 34 | 30 | 34 | 0 | 0 | critical | 15000
K | 3 | 34 | 37 | 34 | 37 | 0 | 0 | critical | 205000
| Critical path | ACDEFJK | 37 | weeks
OPTIMISTIC ESTIMATE | [8 empty] | Normal Costs
Task | Most Optimistic | Early Start | Early Finish | Late Start | Late Finish | Slack=LS-ES | Slack= LF-EF |  | 10000
A | 2 | 0 | 2 | 0 | 2 | 0 | 0 | critical | 20000
B | 4 | 2 | 6 | 16 | 20 | 14 | 14 | non-critical | 15000
C | 5 | 2 | 7 | 2 | 7 | 0 | 0 | critical | 45000
D | 6 | 7 | 13 | 7 | 13 | 0 | 0 | critical | 10000
E | 7 | 13 | 20 | 13 | 20 | 0 | 0 | critical | 15000
F | 4 | 20 | 24 | 20 | 24 | 0 | 0 | critical | 20000
G | 3 | 13 | 16 | 21 | 24 | 8 | 8 | non-critical | 10000
H | 2 | 20 | 22 | 22 | 24 | 2 | 2 | non-critical | 5000
I | 2 | 6 | 8 | 22 | 24 | 16 | 16 | non-critical | 40000
J | 3 | 24 | 27 | 24 | 27 | 0 | 0 | critical | 15000
K | 2 | 27 | 29 | 27 | 29 | 0 | 0 | critical | 205000
| Critical path | ACDEFJK | 29 | weeks
PESSIMISTIC ESTIMATE | [8 empty] | Normal Costs
Task | Most Pessimistic | Early Start | Early Finish | Late Start | Late Finish | Slack=LS-ES | Slack= LF-EF |  | 10000
A | 4 | 0 | 4 | 0 | 4 | 0 | 0 | critical | 20000
B | 10 | 4 | 14 | 30 | 40 | 26 | 26 | non-critical | 15000
C | 9 | 4 | 13 | 4 | 13 | 0 | 0 | critical | 45000
D | 16 | 13 | 29 | 13 | 29 | 0 | 0 | critical | 10000
E | 10 | 29 | 39 | 29 | 39 | 0 | 0 | critical | 15000
F | 6 | 39 | 45 | 40 | 46 | 1 | 1 | non-critical | 20000
G | 10 | 29 | 39 | 36 | 46 | 7 | 7 | non-critical | 10000
H | 7 | 39 | 46 | 39 | 46 | 0 | 0 | critical | 5000
I | 2 | 14 | 16 | 44 | 46 | 30 | 30 | non-critical | 40000
J | 14 | 46 | 60 | 46 | 60 | 0 | 0 | critical | 15000
K | 4 | 60 | 64 | 60 | 64 | 0 | 0 | critical | 205000
| New critical path | ACDEHJK | 64 | weeks
AVERAGE TIME ESTIMATE (Equal weights) | [8 empty] | Normal Costs
Task | Average Time | Early Start | Early Finish | Late Start | Late Finish | Slack=LS-ES | Slack= LF-EF |  | 10000
A | 3 | 0 | 3 | 0 | 3 | 0 | 0 | critical | 20000
B | 7 | 3 | 10 | 21 | 28 | 18 | 18 | non-critical | 15000
C | 6.6667 | 3 | 9.6667 | 3 | 9.6667 | 0 | 0 | critical | 45000
D | 9.6667 | 9.6667 | 19.3333 | 9.6667 | 19.3333 | 0 | 0 | critical | 10000
E | 8.6667 | 19.3333 | 28 | 19.3333 | 28 | 0 | 0 | critical | 15000
F | 5 | 28 | 33 | 28 | 33 | 0 | 0 | critical | 20000
G | 6.3333 | 19.3333 | 25.6667 | 26.6667 | 33 | 7.3333 | 7.3333 | non-critical | 10000
H | 4.3333 | 28 | 32.3333 | 28.6667 | 33 | 0.66667 | 0.66667 | non-critical | 5000
I | 2 | 10 | 12 | 31 | 33 | 21 | 21 | non-critical | 40000
J | 7 | 33 | 40 | 33 | 40 | 0 | 0 | critical | 15000
K | 3 | 40 | 43 | 40 | 43 | 0 | 0 | critical | 205000
| Critical path | ACDEFJK | 43 | weeks
AVERAGE TIME ESTIMATE (Unequal weights) | [8 empty] | Normal Costs
Task | Wt. Average Time | Early Start | Early Finish | Late Start | Late Finish | Slack=LS-ES | Slack= LF-EF |  | 10000
A | 3 | 0 | 3 | 0 | 3 | 0 | 0 | critical | 20000
B | 7 | 3 | 10 | 19.5 | 26.5 | 16.5 | 16.5 | non-critical | 15000
C | 6.3333 | 3 | 9.3333 | 3 | 9.3333 | 0 | 0 | critical | 45000
D | 8.3333 | 9.3333 | 17.6667 | 9.3333 | 17.6667 | 0 | 0 | critical | 10000
E | 8.8333 | 17.6667 | 26.5 | 17.6667 | 26.5 | 0 | 0 | critical | 15000
F | 5 | 26.5 | 31.5 | 26.5 | 31.5 | 0 | 0 | critical | 20000
G | 6.1667 | 17.6667 | 23.8333 | 25.3333 | 31.5 | 7.6667 | 7.6667 | non-critical | 10000
H | 4.1667 | 26.5 | 30.6667 | 27.3333 | 31.5 | 0.83333 | 0.83333 | non-critical | 5000
I | 2 | 10 | 12 | 29.5 | 31.5 | 19.5 | 19.5 | non-critical | 40000
J | 5.5 | 31.5 | 37 | 31.5 | 37 | 0 | 0 | critical | 15000
K | 3 | 37 | 40 | 37 | 40 | 0 | 0 | critical | 205000
| Critical path | ACDEFJK | 40 | weeks

## Q8-9-10-11
Q8 | The project duration can rnage from 29 week to 64 weeks with an average of 40 weeks.
Q9,10,11
AVERAGE TIME ESTIMATE (Unequal weights)
Task | Wt. Average Time | Early Start | Early Finish | Late Start | Late Finish | Slack=LS-ES | Slack= LF-EF |  | Most Optimistic | Most Likely | Most Pessimistic | Variance
A | 3 | 0 | 3 | 0 | 3 | 0 | 0 | critical | 2 | 3 | 4 | 0.11111
B | 7 | 3 | 10 | 19.5 | 26.5 | 16.5 | 16.5 | non-critical | 4 | 7 | 10 | 1
C | 6.3333 | 3 | 9.3333 | 3 | 9.3333 | 0 | 0 | critical | 5 | 6 | 9 | 0.44444
D | 8.3333 | 9.3333 | 17.6667 | 9.3333 | 17.6667 | 0 | 0 | critical | 6 | 7 | 16 | 2.7778 | High
E | 8.8333 | 17.6667 | 26.5 | 17.6667 | 26.5 | 0 | 0 | critical | 7 | 9 | 10 | 0.25
F | 5 | 26.5 | 31.5 | 26.5 | 31.5 | 0 | 0 | critical | 4 | 5 | 6 | 0.11111
G | 6.1667 | 17.6667 | 23.8333 | 25.3333 | 31.5 | 7.6667 | 7.6667 | non-critical | 3 | 6 | 10 | 1.3611 | High
H | 4.1667 | 26.5 | 30.6667 | 27.3333 | 31.5 | 0.83333 | 0.83333 | non-critical | 2 | 4 | 7 | 0.69444
I | 2 | 10 | 12 | 29.5 | 31.5 | 19.5 | 19.5 | non-critical | 2 | 2 | 2 | 0
J | 5.5 | 31.5 | 37 | 31.5 | 37 | 0 | 0 | critical | 3 | 4 | 14 | 3.3611 | High
K | 3 | 37 | 40 | 37 | 40 | 0 | 0 | critical | 2 | 3 | 4 | 0.11111
| Critical path | ACDEFJK | 40 | weeks |  | Target Duration | Prob.
| Variance of the critical path |  | 7.1667 |  |  | 35 | 3.09%
| standard dev |  | 2.6771 | weeks |  | 36 | 6.756%
| Target duration |  | 40 | weeks |  | 37 | 13.12%
| Prob. of Completion within the target duration |  | 50% |  |  | 38 | 22.75%
[6 empty] | 39 | 35.44%
[6 empty] | 40 | 50%
[6 empty] | 41 | 64.56%
[6 empty] | 42 | 77.25%
[6 empty] | 43 | 86.88%
[6 empty] | 44 | 93.24%
[6 empty] | 45 | 96.91%
[6 empty] | 46 | 98.75%
[6 empty] | 47 | 99.55%

## 12-13-14-15
Task | Ex.Time | Normal Cost | Total costs (with crashing) | Crash Time | No. of weeks of crash | Marginal Cost ($/week) | No. of weeks remaining
A | 3 | 10000 | 10000 | 3 | 0 |  | 0
B | 7 | 20000 | 25000 | 6 | 1 | 5000 | 1
C | 6.3333 | 15000 | 30000 | 5 | 1.3333 | 11250 | 0.0033333
D | 8.3333 | 45000 | 65000 | 6 | 2.3333 | 8571.4286 | 0.0033333
E | 8.8333 | 10000 | 20000 | 8 | 0.83333 | 12000 | 0.0033333
F | 5 | 15000 | 18000 | 4 | 1 | 3000 | 0
G | 6.1667 | 20000 | 30000 | 4 | 2.1667 | 4615.3846 | 2.1667
H | 4.1667 | 10000 | 15000 | 3 | 1.1667 | 4285.7143 | 0.99667
I | 2 | 5000 | 5000 | 2 | 0 |  | 0
J | 5.5 | 40000 | 50000 | 5 | 0.5 | 20000 | 0
K | 3 | 15000 | 25000 | 2 | 1 | 10000 | 0
205000
|  | Paths | Duration (Week) | F(0.83W) | F(0.17)+H(0.17) | D(2.33W) | K(1) | C(1.33) | E(0.83) | J(0.5)
|  | ACDEFJK | 40 | 39.17 | 39 | 36.67 | 35.67 | 34.34 | 33.51 | 33.01
|  | ACDEHJK | 39.1667 | 39.1667 | 38.9967 | 36.6667 | 35.6667 | 34.3367 | 33.5067 | 33.0067
|  | ACHJK | 22 | 22 | 21.83 | 21.83 | 20.83 | 19.5 | 19.5 | 19
|  | ACDGJK | 32.3333 | 32.3333 | 32.3333 | 30.0033 | 29.0033 | 27.6733 | 27.6733 | 27.1733
|  | ABIJK | 20.5 | 20.5 | 20.5 | 20.5 | 19.5 | 19.5 | 19.5 | 19
|  | ABFJK | 23.5 | 22.67 | 22.5 | 22.5 | 21.5 | 21.5 | 21.5 | 21
|  | Duration Proj. | 40 | 39.17 | 39 | 36.67 | 35.67 | 34.34 | 33.51 | 33.01
|  | Add. Cost | 0 | 2490 | 1238.5714 | 19971.4286 | 10000 | 14962.5 | 9960 | 10000
|  | Total Cost | 205000 | 207490 | 208728.5714 | 228700 | 238700 | 253662.5 | 263622.5 | 273622.5
|  | Duration Proj. | 40 | 39.17 | 39 | 36.67 | 35.67 | 34.34 | 33.51 | 33.01
|  | Total Cost | 205000 | 207490 | 208728.5714 | 228700 | 238700 | 253662.5 | 263622.5 | 273622.5